## LRE Project List
Appendix 1 - Project List & Summaries
|  |  |  | MVA Released (ED2) |  |  | MVA Released (ED3)
|  |  | Licence Area | Baseline | Total Forecast | Forecast Additional MVA released | Total Forecast (ED3)
|  |  | SEPD | 1039 | 1642.8527 | 603.8527 | 4161.43
|  |  | SHEPD | 202 | 379.8113 | 177.8113 | 639.842
|  |  | Total | 1241 | 2022.664 | 781.664 | 4801.272
Expenditure (ED2)
|  |  | Licence Area | 2026 £m | 2027 £m | 2028 £m | ED2 Y 3-5 £m
SEPD
|  |  | Target Completion in ED2 |  |  |  | 142.2347
|  |  | Start in ED2, Complete in ED3 |  |  |  | 291.8712
SHEPD
|  |  | Target Completion in ED2 |  |  |  | 187.4735
|  |  | Start in ED2, Complete in ED3 |  |  |  | 63.0549
|  |  | Total |  |  |  | 684.6343
Licence Area | Project Reference | Project Name | Driver | Project Category | Cost Bucket | Project Development | In Previous Business Plan? | Project Summary | EJP Submitted | EJP Reference | CBA Submitted | CBA Reference | CEM Submitted | CEM Reference
SEPD | PS005432 | GR Witney Town Witney Town Transformer Upgrade (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 1. Green Recovery | 2. Yes - ED2 |  | No |  | No |  | No
SEPD | PS005433 | GR Wheatley Wheatley Transformer and Connection Upgrade (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 1. Green Recovery | 2. Yes - ED2 |  | No |  | No |  | No
SEPD | PS005435 | GR North Baddesley Tx and connection upgrade (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 1. Green Recovery | 2. Yes - ED2 |  | No |  | No |  | No
SEPD | PS005436 | GR Bishops Waltham Tx and connection upgrade (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 1. Green Recovery | 2. Yes - ED2 |  | No |  | No |  | No
SEPD | PS005525 | GR Rownhams Motorway Service Area (MSA) - Rownhams 33kV network (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 1. Green Recovery | 2. Yes - ED2 |  | No |  | No |  | No
SHEPD | PH002548 | Opt 3 (S) / St Fergus Gas 11kV Switchboard Replacement North Caledonia (P) | CV3 - Fault Level Reinforcement | 1. Target Completion in ED2 |  | 2. Existing Scheme | 1. Yes - ED1 |  | No |  | No |  | No
SHEPD | PH002729 | Longman Drive Primary Substation Inverness GSP (P) / Opt 3 Jacobs (S) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 2. Existing Scheme | 1. Yes - ED1 |  | No |  | No |  | No
SHEPD | PH002730 | ED2 (S) / South Elgin Strategy Cumming Street, Ashgrove & Bilbohall (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 2. Existing Scheme | 1. Yes - ED1 |  | No |  | No |  | No
SHEPD | PH003127 | OPT 3 Motts (S) / Rothienorrman GSP - Gordonstown W/F Cabling Aberdeenshire (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 2. Existing Scheme | 1. Yes - ED1 |  | No |  | No |  | No
SHEPD | PH003128 | OPT 3 Motts (S) / Rothienorrman GSP - Glens of Foudland W/F Cabling Aberdeenshire (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 2. Existing Scheme | 1. Yes - ED1 |  | No |  | No |  | No
SHEPD | PH003197 | OPT 3 Motts (S) / Rothienorrman GSP - Insch Pri Integration Works Aberdeenshire (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 2. Existing Scheme | 1. Yes - ED1 |  | No |  | No |  | No
SHEPD | PH003198 | OPT 3 Motts (S) / Rothienorrman GSP - Fyvie Pri Integration Works Aberdeenshire (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 2. Existing Scheme | 1. Yes - ED1 |  | No |  | No |  | No
SEPD | PS001272 | Shripney - Bilsham OHL Overlay - (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 2. Existing Scheme | 1. Yes - ED1 |  | No |  | No |  | No
SEPD | PS001335 | Shripney - ARGR - SBER - Under Grounding 33kV Circuits - (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 2. Existing Scheme | 1. Yes - ED1 |  | No |  | No |  | No
SEPD | PS002022 | PETE E1L5 Petersfield Town Centre (P) | CV3 - Fault Level Reinforcement | 1. Target Completion in ED2 |  | 2. Existing Scheme | 1. Yes - ED1 |  | No |  | No |  | No
SEPD | PS002140 | Coxmoor Wood Rutter pole replacement (P) / Crookham (S) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 2. Existing Scheme | 1. Yes - ED1 |  | No |  | No |  | No
SEPD | PS002236 | Canal Bank 22/6.6kV System Reinforcement - (P) / Wesltey Avenue 11kV Substation (S) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 2. Existing Scheme | 1. Yes - ED1 |  | No |  | No |  | No
SEPD | PS002593 | Upper Heyford Bicester (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 2. Existing Scheme | 1. Yes - ED1 |  | No |  | No |  | No
SEPD | PS002677 | High Wycombe E7L5 Clifton Court S/S (P) | CV3 - Fault Level Reinforcement | 1. Target Completion in ED2 |  | 2. Existing Scheme | 1. Yes - ED1 |  | No |  | No |  | No
SEPD | PS003180 | UPPH E4L5 Upper Heyford (P) | CV3 - Fault Level Reinforcement | 1. Target Completion in ED2 |  | 2. Existing Scheme | 1. Yes - ED1 |  | No |  | No |  | No
SEPD | PS003512 | Taplow E5L5 (P) | CV3 - Fault Level Reinforcement | 1. Target Completion in ED2 |  | 2. Existing Scheme | 1. Yes - ED1 |  | No |  | No |  | No
SEPD | PS003661 | Rownhams - North Baddesley 33 kV network reinforcement - (P) / UG33 (S) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 2. Existing Scheme | 1. Yes - ED1 |  | No |  | No |  | No
SEPD | PS004326 | Southfield Road 66/11 kV transformer replacement (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 2. Existing Scheme | 1. Yes - ED1 |  | No |  | No |  | No
SEPD | PS004509 | Pangbourne E3L5 (P) | CV3 - Fault Level Reinforcement | 1. Target Completion in ED2 |  | 2. Existing Scheme | 1. Yes - ED1 |  | No |  | No |  | No
SEPD | PS006568 | Fernhurst Fernhurst (P) / Five Oaks (S) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 2. Existing Scheme | 1. Yes - ED1 |  | No |  | No |  | No
SEPD | PS006569 | Coxmoor Wood Wrecclesham (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 2. Existing Scheme | 1. Yes - ED1 |  | No |  | No |  | No
SEPD | PS006571 | Havant Horndean (P) / Waterlooville Horndean (S) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 2. Existing Scheme | 1. Yes - ED1 |  | No |  | No |  | No
SEPD | PS006745 | Trash Green E4L5 Burghfield, READING (P) | CV3 - Fault Level Reinforcement | 1. Target Completion in ED2 |  | 2. Existing Scheme | 1. Yes - ED1 |  | No |  | No |  | No
SEPD | PS009167 | Fort Widley - 132 kV - 132/33 kV Transformer Replacement Fort Widley (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 2. Existing Scheme | 1. Yes - ED1 | Transfers Horndean to Fort Widley, upgrades circuits and transformers, and uses flexibility to defer investment. Releases __MVA and supports compliance to 2050. | Yes | SEPD_CV1_PS009167, PS009168_Lovedean_Fort Widley - Horndean - Waterlooville_EJP | Yes | SEPD_CV1_PS009167, PS009168_Lovedean_Fort Widley - Horndean - Waterlooville_CBA | Yes | SEPD_CV1_PS009167_Lovedean_Fort Widley - Horndean - Waterlooville_CEM
SHEPD | PH002544 | A&W Taynuilt - Tullich Argyll (P) / Opt 3 Motts (S) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 2. Existing Scheme | 2. Yes - ED2 |  | No |  | No |  | No
SHEPD | PH002739 | Aboyne & Ballater 11kV network reinforcement North Caledonia (P) / Opt 3 Motts (S) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 2. Existing Scheme | 2. Yes - ED2 |  | No |  | No |  | No
SHEPD | PH003482 | New Pitsligo Aberdeenshire (P) / Transformer Replacement (S) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 2. Existing Scheme | 2. Yes - ED2 |  | No |  | No |  | No
SHEPD | PH003588 | Shetland GSP and 33kV Network Integration Works Shetland, North Caledonia (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 2. Existing Scheme | 2. Yes - ED2 |  | No |  | No |  | No
SHEPD | PH004120 | The Shetland Intergrated Power Solution North Caledonia (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 2. Existing Scheme | 2. Yes - ED2 |  | No |  | No |  | No
SHEPD | PH004149 | 33kV North Shetland Strategy Shetland, North Caledonia (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 2. Existing Scheme | 2. Yes - ED2 | Reinforce the electricity network North of Lerwick to address voltage constraints and support future demand, by integrating new circuits and installing reactive compensation. The preferred investment will deliver increased network capacity and resilience for the Shetland Isles. | Yes | SHEPD_CV1_PH004149_Shetland_North Shetland_EJP | Yes | SHEPD_CV1_PH004149_Shetland_North Shetland_CBA | No
SHEPD | PH004284 | Insch 001,002,003,007,008,009 HV Feeder Fault Level Reinforcement (P) | CV3 - Fault Level Reinforcement | 1. Target Completion in ED2 |  | 2. Existing Scheme | 2. Yes - ED2 |  | No |  | No |  | No
SEPD | PS000663 | Leamington Park Substation - Uprate 6.6kV Network to 11kV - C1744580 - (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 2. Existing Scheme | 2. Yes - ED2 |  | No |  | No |  | No
SEPD | PS002277 | 132 kV reinforcement Thatcham (S) / Bramley - Thatcham Ashford Hill (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 2. Existing Scheme | 2. Yes - ED2 |  | No |  | No |  | No
SEPD | PS004941 | Netley Common BSP 132/33 kV transformer reinforcement Netley Common BSP (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 2. Existing Scheme | 2. Yes - ED2 |  | No |  | No |  | No
SEPD | PS005024 | Alton Fernhurst Split-second phase Budds Lane (S) / Borden-Budds Lane-Alton Borden (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 2. Existing Scheme | 2. Yes - ED2 |  | No |  | No |  | No
SEPD | PS005552 | 33kV Rutter pole replacement Aldershot (S) / Aldershot Farnham (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 2. Existing Scheme | 2. Yes - ED2 |  | No |  | No |  | No
SHEPD | PH003076 | Balaldie 11kV Network Alness GSP (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 3. Change of Scope | 2. Yes - ED2 | Reinforcement of Balaldie primary substation 11kV networks to address security of supply and voltage issues, ensuring compliance and future-proofing the network. | Yes | SHEPD_CV1_PH003076_Alness_Balaldie CCT_EJP | Yes | SHEPD_CV1_PH003076_Alness_Balaldie CCT_CBA | No
SHEPD | PH003692 | Harris Grid/Loch Carnan 33kV Circuits - Highlands and Islands (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 3. Change of Scope | 2. Yes - ED2 |  | No |  | No |  | No
SHEPD | PH003701 | Halkirk 33/11kV Transformer - H&I (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 3. Change of Scope | 2. Yes - ED2 | Replacement of Halkirk T1 with 2x 6.3MVA units, 11kV reinforcement, and flexibility to avoid thermal overload until reinforcement is delivered. | Yes | SHEPD_CV1_PH003701_Thurso South_Halkirk Primary_EJP | Yes | SHEPD_CV1_PH003701_Thurso South_Halkirk Primary_CBA | Yes | SHEPD_CV1_PH003701_Thurso South_Halkirk Primary_CEM
SHEPD | PH004272 | KEITH 33kV Circuits Keith 2 GSP CapEx Enhancement (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 3. Change of Scope | 2. Yes - ED2 |  | No |  | No |  | No
SHEPD | PH004363 | Brodick-Balliekine 33kV/11kV Reinforcements Lochranza New Primary, Isle of Arran (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 3. Change of Scope | 2. Yes - ED2 | New primary at Lochranza to split Brodick-Balliekine 11kV circuits, resolving voltage and thermal issues up to 2050. | Yes | SHEPD_CV1_PH004363_Carradale_Brodick - Balliekine CCT_EJP | Yes | SHEPD_CV1_PH004363_Carradale_Brodick - Balliekine CCT_CBA | No
SHEPD | PH004365 | Oban 33kV Circuits Taynuilt GSP (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 3. Change of Scope | 2. Yes - ED2 |  | No |  | No |  | No
SHEPD | PH004407 | Dunvegan 33kV Ccts - Highlands and Islands (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 3. Change of Scope | 2. Yes - ED2 | Upgrade of overhead lines, dynamic compensation, and new primary substation at Brogaig to resolve voltage and P2/8 compliance issues. | Yes | SHEPD_CV1_PH004407_Dunvegan_Dunvegan GSP_EJP | Yes | SHEPD_CV1_PH004407_Dunvegan_Dunvegan GSP_CBA | No
SHEPD | PH004408 | ED2 (S) / St. Mary's OHL/Tx Reinforcement Orkney (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 3. Change of Scope | 2. Yes - ED2 | Establish a new primary S/S at Grimness on South Ronaldsay and install two 4MVA primary transformers. Required to maintain compliance with P2/8. | Yes | SHEPD_CV1_PH004408_Thurso South_St Marys Primary_EJP | Yes | SHEPD_CV1_PH004408_Thurso South_St Marys Primary_CBA | No
SHEPD | PH004429 | Lochgilphead 1L5 and Carradale 5L5 Circuit Reinforcement Argyll and Bute (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 3. Change of Scope | 2. Yes - ED2 | Multi-scheme reinforcement for Cromalt/Inveraray, Lochgilphead/Carradale, and Islay, addressing thermal, voltage, and P2/8 issues. | Yes | SHEPD_CV1_PH003794, PH004419, PH004429_PORT ANN_PORT ANN GSP_EJP | No |  | No
SEPD | PS007683 | East Bedfont 132/22kV Transformer Reinforcement (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 3. Change of Scope | 2. Yes - ED2 | Replaces two 60MVA transformers with 90MVA units to resolve thermal overload and asset health issues, ensuring compliance and releasing __MVA capacity. | Yes | SEPD_CV1_PS007683_Laleham_East Bedfont_EJP | Yes | SEPD_CV1_PS007683_Laleham_East Bedfont_CBA | Yes | SEPD_CV1_PS007683_Laleham_East Bedfont_CEM
SEPD | PS007695 | Harvard Lane Transformer Primary Reinforcement (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 3. Change of Scope | 2. Yes - ED2 | Upgrades Harvard Lane Primary to address load growth and security of supply, including new cables, transformers, and flexibility. Delivers a __MVA capacity increase and supports compliance to 2050. | Yes | SEPD_CV1_PS007695_Ealing_Ealing – Harvard Lane_EJP | Yes | SEPD_CV1_PS007695_Ealing_Ealing – Harvard Lane_CBA | Yes | SEPD_CV1_PS007695_Ealing_Ealing – Harvard Lane_CEM
SEPD | PS007703 | Alresford transformer and 33kV circuit reinforcement Alresford (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 3. Change of Scope | 2. Yes - ED2 | Addresses transformer and circuit overloads, driven by forecast demand. Delivers new transformers, OHL reinforcement, and flexibility, releasing up to __MVA by 2029 and securing compliance until 2044. | Yes | SEPD_CV1_PS007703_Fleet_Alresford Primary_EJP | No |  | No
SEPD | PS007706 | Denham 132kV Circuit Reinforcement (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 3. Change of Scope | 2. Yes - ED2 |  | No |  | No |  | No
SEPD | PS008895 | 33/11kV transformers upgrade (S) / Swanage Primary under Wareham BSP (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 3. Change of Scope | 2. Yes - ED2 | Reinforcement of Swanage primary substation to address thermal overloading and security of supply issues. The preferred option combines flexibility services with targeted reinforcements, delivering increased capacity and P2 compliance. | Yes | SEPD_CV1_PS008895_Mannington_Wareham (Swanage)_EJP | Yes | SEPD_CV1_PS008895_Mannington_Wareham (Swanage)_CBA | No
SEPD | PS009059 | Bitterne Primary (S) / 7x 33kV Indoor CB Netley Common BSP (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 3. Change of Scope | 2. Yes - ED2 | Addresses thermal constraints in a ringed 33kV network with phased switchgear upgrades, new cables, and flexibility. Releases over __MVA of capacity by 2032, supporting compliance and growth. | Yes | SEPD_CV1_PS009086, PS009059_Botley Wood_Netley Common CCT_EJP | Yes | SEPD_CV1_PS009086, PS009059_Botley Wood_Netley Common CCT_CBA | No
SEPD | PS009086 | 2x cct, 2 outdoor CBs NETC Weston Primary (P) / Circuit overlay NETC Woolston Primary (S) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 3. Change of Scope | 2. Yes - ED2 | Addresses thermal constraints in a ringed 33kV network with phased switchgear upgrades, new cables, and flexibility. Releases over __MVA of capacity by 2032, supporting compliance and growth. | Yes | SEPD_CV1_PS009086, PS009059_Botley Wood_Netley Common CCT_EJP | Yes | SEPD_CV1_PS009086, PS009059_Botley Wood_Netley Common CCT_CBA | Yes | SEPD_CV1_PS009086_Botley Wood_Netley Common CCT_CEM
SEPD | PS009350 | Chippenham Melksham (P) / Fault level switchboard replacement EJP (S) | CV3 - Fault Level Reinforcement | 1. Target Completion in ED2 |  | 3. Change of Scope | 2. Yes - ED2 | Installs new indoor switchboard to resolve fault level issues and enable future generation connections at Chippenham BSP. | Yes | SEPD_CV3_PS009350_Melksham_Chippenham BSP_EJP | No |  | No
SHEPD | PH004210 | Dyce_Ellon Dyce GSP (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 4. New Scheme | 3. No | Transformer and switchgear replacement, STATCOM installation, and OHL re-rating to resolve voltage and thermal issues at Ellon. | Yes | SHEPD_CV1_PH004210_Dyce_Dyce - Ellon CCT_EJP | No |  | No
SHEPD | PH004222 | Braco West / Callander 33kV STATCOM - Braco Grid GSP (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 4. New Scheme | 3. No | STATCOM installation and OHL reinforcement to resolve voltage issues at Callander and Kippen. | Yes | SHEPD_CV1_PH004222_Braco West_Braco West - Callander STATCOM _EJP | Yes | SHEPD_CV1_PH004222_Braco West_Braco West - Callander STATCOM _CBA | No
SHEPD | PH004227 | Coshieville Primary TX - Tummel Bridge Grid (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SHEPD | PH004273 | A&W Machrie T2, 11kV Switchboard and Voltage Regulator Isle of Arran (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 4. New Scheme | 3. No | Reinforcement of Machrie and Brodick Primaries to address voltage and thermal issues, including STATCOMs and transformer upgrade. | Yes | SHEPD_CV1_PH004273_Carradale_Arran CCT_EJP | Yes | SHEPD_CV1_PH004273_Carradale_Arran CCT_CBA | No
SHEPD | PH004285 | Fyvie 003,004 HV Feeder Fault Level Reinforcement (P) | CV3 - Fault Level Reinforcement | 1. Target Completion in ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SHEPD | PH004289 | Waterloo Place Reinforcement Waterloo Place Primary (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SHEPD | PH004311 | Springhill Primary Transformer Replacement Woodhill GSP (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SHEPD | PH004336 | Kingseat T1+T2 Replacement (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SHEPD | PH004411 | Drymen and Killearn 33/11kV Substations Strathleven GSP (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SHEPD | PH004615 | Firth Primary S/S Reinforcement North Caledonia (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SHEPD | PH004627 | NAIRN 33kV Circuits H&I (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 4. New Scheme | 3. No | Multi-scheme reinforcement for Nairn and Forres, including cable upgrades, transformer replacement, and flexibility. | Yes | SHEPD_CV1_PH004627_Nairn_Nairn CCT_EJP | Yes | SHEPD_CV1_PH004627_Nairn_Nairn CCT_CBA | No
SEPD | PS004169 | HVUR 77006 PETE E1L5 Petersfield Square (P) | CV3 - Fault Level Reinforcement | 1. Target Completion in ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SEPD | PS007182 | 90MVA 132kV Transformer Thatcham Thatcham (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 4. New Scheme | 3. No | Installs a new 90MVA transformer and associated switchgear, using flexibility to defer investment, ensuring P2/8 compliance and releasing __MVA. | Yes | SEPD_CV1_PS007182_Bramley_Thatcham CCT_EJP | Yes | SEPD_CV1_PS007182_Bramley_Thatcham CCT_CBA | Yes | SEPD_CV1_PS007182_Bramley_Thatcham CCT_CEM
SEPD | PS007689 | Wimborne 33/11 kV Primary Transformers replacement (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SEPD | PS007705 | Aldershot - (P) / Tongham 33kV Circuit Primary Reinforcement (S) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 4. New Scheme | 3. No | Installs new underground cables and circuit breaker to replace rutter pole circuits, improving security of supply and releasing __MVA. | Yes | SEPD_CV1_PS007705_Fleet_Fleet - Tongham CCT_EJP | Yes | SEPD_CV1_PS007705_Fleet_Fleet - Tongham CCT_CBA | No
SEPD | PS008853 | Uxbridge PSS Strategic Investment (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 4. New Scheme | 3. No | Upgrades three 28MVA transformers to 40MVA units, increasing firm capacity to 76.2MVA and supporting forecasted load growth until 2036. | Yes | SEPD_CV1_PS008853_Iver 66kV_Uxbridge Primary_EJP | No |  | No
SEPD | PS009027 | Central Bridge - Old Docks 33kV cct overlay - Central Bridge Primary (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 4. New Scheme | 3. No | Constructs a new BSP, upgrades circuits and switchgear, and uses flexibility to defer some investments. Releases __MVA at BSP and supports major port growth. | Yes | SEPD_CV1_PS009027, PS009159, PS009161, PS009028_Nursling_Southampton BSP _EJP | Yes | SEPD_CV1_PS009027, PS009159, PS009161, PS009028_Nursling_Southampton BSP _CBA | No
SEPD | PS009029 | Romsey PSS Tx upgrade - Romsey 33/11kV Substation (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SEPD | PS009069 | FAJ153 Witney 132kV EJP (S) / PKFAJ153 Witney 132kV EJP (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 4. New Scheme | 3. No | Reconductors 132kV circuits, adds a third transformer, and upgrades switchgear to resolve thermal constraints and support growth to 2050. | Yes | SEPD_CV1_PS009069_Cowley_Witney BSP_EJP | Yes | SEPD_CV1_PS009069_Cowley_Witney BSP_CBA | No
SEPD | PS009135 | EJP Cowley Local 132kV network reinforcement (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 4. New Scheme | 3. No | Installs new transformer, circuits, and switchgear, upgrades Rose Hill, and uses flexibility to defer investment, ensuring compliance and capacity. | Yes | SEPD_CV1_PS009152, PS009135_Cowley_Cowley Local Main and 132kV CCT_EJP | Yes | SEPD_CV1_PS009152, PS009135_Cowley_Cowley Local Main and 132kV CCT_CBA | Yes | SEPD_CV1_PS009135_Cowley_Cowley Local Main and 132kV CCT_CEM SEPD_CV1_PS009135_Cowley_Cowley Local Main and 132kV CCT_CEM2
SEPD | PS009204 | Chichester PSS Transformer Reinforcement (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SEPD | PS009206 | South Bersted PSS Transformer Reinforcement (P) | CV1 - Primary Reinforcement | 1. Target Completion in ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SEPD | PS009412 | Titchfield E4L5 Crofton s/s & Sumar Close PMT (P) | CV3 - Fault Level Reinforcement | 1. Target Completion in ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SEPD | PS004659 | Iver 132 kV Fault Level Replacement Scheme (P) | CV3 - Fault Level Reinforcement | 2. Start in ED2, Complete in ED3 |  | 2. Existing Scheme | 2. Yes - ED2 |  | No |  | No |  | No
SEPD | PS007694 | Lytchett 33kV circuit breaker reinforcement (P) | CV3 - Fault Level Reinforcement | 2. Start in ED2, Complete in ED3 |  | 2. Existing Scheme | 2. Yes - ED2 | Reinforces Lytchett with new transformers and switchgear to resolve fault level and thermal constraints, supporting growth and connections. | Yes | SEPD_CV3_PS007694_Mannington_Lytchett 33kV CB_EJP | Yes | SEPD_CV3_PS007694_Mannington_Lytchett 33kV CB_CBA | No
SEPD | PS003152 | Alton-Fernhurst 132 kV Alton (P) / SCO Reinforcement Fernhurst (S) | CV1 - Primary Reinforcement | 2. Start in ED2, Complete in ED3 |  | 3. Change of Scope | 1. Yes - ED1 | Resolves security of supply non-compliance for Alton & Fernhurst by installing a new GIS switchboard, underground cables, and associated works. Creates __MVA of new capacity. | Yes | SEPD_CV1_PS003152_Fleet_Alton - Fernhurst CCT_EJP | Yes | SEPD_CV1_PS003152_Fleet_Alton - Fernhurst CCT_CBA | No
SHEPD | PH004212 | KEITH 33 kV Circuits Keith 1 GSP (P) | CV1 - Primary Reinforcement | 2. Start in ED2, Complete in ED3 |  | 3. Change of Scope | 2. Yes - ED2 | Combination of reconfiguration, network extension, and reinforcement to resolve voltage issues and support future load growth. | Yes | SHEPD_CV1_PH004212_Keith_Keith 1 CCT_EJP | Yes | SHEPD_CV1_PH004212_Keith_Keith 1 CCT_CBA | No
SHEPD | PH004240 | Culloden Primary Substation Reinforcement (P) | CV1 - Primary Reinforcement | 2. Start in ED2, Complete in ED3 |  | 3. Change of Scope | 2. Yes - ED2 | Reinforcement of Culloden Primary transformers and switchgear, with flexibility to defer reinforcement, ensuring compliance up to 2050. | Yes | SHEPD_CV1_PH004240_Inverness_Culloden Primary_EJP | Yes | SHEPD_CV1_PH004240_Inverness_Culloden Primary_CBA | Yes | SHEPD_CV1_PH004240_Inverness_Culloden Primary_CEM
SHEPD | PH004303 | ED2 (S) / Stornoway 33kV 305 Circuit Reinforcement Highlands & Islands (P) | CV1 - Primary Reinforcement | 2. Start in ED2, Complete in ED3 |  | 3. Change of Scope | 2. Yes - ED2 | Installation of 4MVAr STATCOM and repositioning of NOP to resolve voltage issues and improve P2/8 compliance. | Yes | SHEPD_CV1_PH004303_Stornoway_Stornoway CCT_EJP | No |  | No
SHEPD | PH004343 | Elgin Ashgrove Circuits & Transformer Elgin GSP (P) | CV1 - Primary Reinforcement | 2. Start in ED2, Complete in ED3 |  | 3. Change of Scope | 2. Yes - ED2 | Combination of flexibility and reinforcement for Ashgrove 33kV circuits, including new transformers and switchgear. | Yes | SHEPD_CV1_PH004343_Elgin_Elgin - Ashgrove CCT_EJP | Yes | SHEPD_CV1_PH004343_Elgin_Elgin - Ashgrove CCT_CBA | Yes | SHEPD_CV1_PH004343_Elgin_Elgin - Ashgrove CCT_CEM
SHEPD | PH004383 | Burghmuir 33kV Cct Reinforcement (P) | CV1 - Primary Reinforcement | 2. Start in ED2, Complete in ED3 |  | 3. Change of Scope | 2. Yes - ED2 | Reinforcement of Burghmuir GSP network to resolve thermal overloads, with flexibility to defer investment. | Yes | SHEPD_CV1_PH004383_Burghmuir_Burghmuir CCT_EJP | Yes | SHEPD_CV1_PH004383_Burghmuir_Burghmuir CCT_CBA | Yes | SHEPD_CV1_PH004383_Burghmuir_Burghmuir CCT_CEM
SHEPD | PH004420 | ED2 (S) / Skulamus Primary Substation P2 Scheme Skulamus (P) | CV1 - Primary Reinforcement | 2. Start in ED2, Complete in ED3 |  | 3. Change of Scope | 2. Yes - ED2 | Replacement of Skulamus Primary with 2x 6.3MVA, 33kV primary, 11kV reinforcement, new switch room at Broadford GSP. | Yes | SHEPD_CV1_PH004420_Broadford_Broaford - Skulamus CCT_EJP | Yes | SHEPD_CV1_PH004420_Broadford_Broaford - Skulamus CCT_CBA | No
SHEPD | PH004437 | Finstown Integration H&I (P) | CV1 - Primary Reinforcement | 2. Start in ED2, Complete in ED3 |  | 3. Change of Scope | 2. Yes - ED2 | Integration of new Finstown GSP into Orkney network, reinforcing circuits to meet future demand and improve security of supply. | Yes | SHEPD_CV1_PH004437_Thurso South_Finstown CCT_EJP | No |  | No
SHEPD | PH004442 | Abernethy GSP & Milnathort Primary (P) | CV1 - Primary Reinforcement | 2. Start in ED2, Complete in ED3 |  | 3. Change of Scope | 2. Yes - ED2 | Major reinforcement of 33kV network to address future thermal and voltage issues. | Yes | SHEPD_CV1_PH004442_Abernethy_Abernethy CCT_EJP | Yes | SHEPD_CV1_PH004442_Abernethy_Abernethy CCT_CBA | Yes | SHEPD_CV1_PH004442_Abernethy_Abernethy CCT_CEM
SEPD | PS006702 | Fleet Bramley split - 132 kV - strategic investment/Bramley Bramley (P) | CV1 - Primary Reinforcement | 2. Start in ED2, Complete in ED3 |  | 3. Change of Scope | 2. Yes - ED2 | Splits Fleet–Bramley group to avoid Class F demand, installing new switchboards, cables, and using flexibility to expedite connections. Supports compliance and future expansion. | Yes | SEPD_CV1_PS006702_Fleet_Fleet - Bramley Split_EJP | Yes | SEPD_CV1_PS006702_Fleet_Fleet - Bramley Split_CBA | No
SEPD | PS007702 | Ashton Park 33kV Circuit Reinforcement (P) | CV1 - Primary Reinforcement | 2. Start in ED2, Complete in ED3 |  | 3. Change of Scope | 2. Yes - ED2 | Adds new cables, switchgear, and transformer, reconfigures circuits, and uses flexibility to defer investment, ensuring P2 and P18 compliance. | Yes | SEPD_CV1_PS007702_Melksham_Ashton Park_EJP | Yes | SEPD_CV1_PS007702_Melksham_Ashton Park_CBA | Yes | SEPD_CV1_PS007702_Melksham_Ashton Park_CEM
SEPD | PS008844 | Denham BSP Strategic Investment (P) | CV1 - Primary Reinforcement | 2. Start in ED2, Complete in ED3 |  | 3. Change of Scope | 2. Yes - ED2 | Reinforces Denham BSP and downstream primaries to resolve thermal overloads and rationalise voltage levels. Delivers __MVA at Denham and __MVA at each primary. | Yes | SEPD_CV1_PS009024, PS009022, PS008844_Iver 132kV_Denham BSP_EJP | Yes | SEPD_CV1_PS009024, PS009022, PS008844_Iver 132kV_Denham BSP_CBA | No
SEPD | PS008906 | ED2 EJP Stokenchurch 33kV network reinforcement (P) | CV1 - Primary Reinforcement | 2. Start in ED2, Complete in ED3 |  | 3. Change of Scope | 2. Yes - ED2 | Reinforces the 33kV ring and Watlington transformer to resolve forecast overloads, using flexibility to defer investment. Delivers __MVA (ring) and __MVA (WATL). | Yes | SEPD_CV1_PS008906_Cowley_Stokenchurch_EJP | Yes | SEPD_CV1_PS008906_Cowley_Stokenchurch_CBA, SEPD_CV1_PS008906_Cowley_Stokenchurch_CBA | Yes | SEPD_CV1_PS008906_Cowley_Stokenchurch_CEM SEPD_CV1_PS008906_Cowley_Stokenchurch_CEM2
SEPD | PS008953 | 33kV OHL reinforcement HUNSTON BSP to BIRDHAM PSS (P) / rutter pole replacement (S) | CV1 - Primary Reinforcement | 2. Start in ED2, Complete in ED3 |  | 3. Change of Scope | 2. Yes - ED2 | Replaces OHLs with UG cables, upgrades transformers, and uses flexibility to defer investment, resolving operational and thermal issues for Birdham and Selsey. | Yes | SEPD_CV1_PS008953, PS008954_Lovedean_Hunston BSP - Birdham & Selsey Primaries_EJP | Yes | SEPD_CV1_PS008953, PS008954_Lovedean_Hunston BSP - Birdham & Selsey Primaries_CBA | No
SEPD | PS008954 | 33kV OHL reinforcement HUNSTON BSP to Selsey PSS (P) / rutter pole replacement (S) | CV1 - Primary Reinforcement | 2. Start in ED2, Complete in ED3 |  | 3. Change of Scope | 2. Yes - ED2 | Replaces OHLs with UG cables, upgrades transformers, and uses flexibility to defer investment, resolving operational and thermal issues for Birdham and Selsey. | Yes | SEPD_CV1_PS008953, PS008954_Lovedean_Hunston BSP - Birdham & Selsey Primaries_EJP | Yes | SEPD_CV1_PS008953, PS008954_Lovedean_Hunston BSP - Birdham & Selsey Primaries_CBA | No
SEPD | PS009028 | new Southampton BSP + dual 132kV cct from Nursling GSP - Southampton BSP (P) | CV1 - Primary Reinforcement | 2. Start in ED2, Complete in ED3 |  | 3. Change of Scope | 2. Yes - ED2 | Constructs a new BSP, upgrades circuits and switchgear, and uses flexibility to defer some investments. Releases __MVA at BSP and supports major port growth. | Yes | SEPD_CV1_PS009027, PS009159, PS009161, PS009028_Nursling_Southampton BSP _EJP | Yes | SEPD_CV1_PS009027, PS009159, PS009161, PS009028_Nursling_Southampton BSP _CBA | Yes | SEPD_CV1_PS009028_Nursling_Southampton BSP _CEM
SEPD | PS009048 | 33kV Reinforcements (S) / Faringdon EJP (P) | CV1 - Primary Reinforcement | 2. Start in ED2, Complete in ED3 |  | 3. Change of Scope | 2. Yes - ED2 | Installs new cable and transformers to resolve thermal and voltage issues, ensuring P2/8 compliance to at least 2035. Releases __MVA. | Yes | SEPD_CV1_PS009048_Minety_Faringdon CCT_EJP | No |  | No
SEPD | PS009159 | new Southampton - Central Bridge 33kV cct reinforcement - Southampton BSP (P) | CV1 - Primary Reinforcement | 2. Start in ED2, Complete in ED3 |  | 3. Change of Scope | 2. Yes - ED2 | Constructs a new BSP, upgrades circuits and switchgear, and uses flexibility to defer some investments. Releases __MVA at BSP and supports major port growth. | Yes | SEPD_CV1_PS009027, PS009159, PS009161, PS009028_Nursling_Southampton BSP _EJP | Yes | SEPD_CV1_PS009027, PS009159, PS009161, PS009028_Nursling_Southampton BSP _CBA | Yes | SEPD_CV1_PS009159_Nursling_Southampton BSP _CEM
SEPD | PS009161 | Southampton Main/Reserve BSP 33kV indoor switchboard + new BSP 33kV indoor switchboard - Southampton BSP (P) | CV1 - Primary Reinforcement | 2. Start in ED2, Complete in ED3 |  | 3. Change of Scope | 2. Yes - ED2 | Constructs a new BSP, upgrades circuits and switchgear, and uses flexibility to defer some investments. Releases __MVA at BSP and supports major port growth. | Yes | SEPD_CV1_PS009027, PS009159, PS009161, PS009028_Nursling_Southampton BSP _EJP | Yes | SEPD_CV1_PS009027, PS009159, PS009161, PS009028_Nursling_Southampton BSP _CBA | No
SEPD | PS009211 | BRAMLEY THATCHAM AMESBURY - 132kV Bramley (P) / Load Reinforcement EJP (S) | CV1 - Primary Reinforcement | 2. Start in ED2, Complete in ED3 |  | 3. Change of Scope | 2. Yes - ED2 | Lays new 132kV cable circuits and switchgear to resolve FCO non-compliance, releasing __MVA and ensuring compliance to at least 2036/37. | Yes | SEPD_CV1_PS009211_Bramley_Bramley - Thatcham - Amesbury CCT_EJP | Yes | SEPD_CV1_PS009211_Bramley_Bramley - Thatcham - Amesbury CCT_CBA | No
SEPD | PS009219 | Dual 33kV ccts from SALI BSP to PETF PSS Petersfinger PSS (P) | CV1 - Primary Reinforcement | 2. Start in ED2, Complete in ED3 |  | 3. Change of Scope | 2. Yes - ED2 | Isolates Netherhampton and Petersfinger from the ring, upgrades transformers, and uses flexibility to defer investment. Ensures compliance and releases __MVA. | Yes | SEPD_CV1_PS009219, PS009220, PS009222_Mannington_Bemerton CCT_EJP | Yes | SEPD_CV1_PS009219, PS009220, PS009222_Mannington_Bemerton CCT_CBA | Yes | SEPD_CV1_PS009219_Mannington_Bemerton CCT_CEM
SEPD | PS009220 | Dual 33kV circuit from SALI BSP to NETH PSS SALI BSP NETH PSS (P) | CV1 - Primary Reinforcement | 2. Start in ED2, Complete in ED3 |  | 3. Change of Scope | 2. Yes - ED2 | Isolates Netherhampton and Petersfinger from the ring, upgrades transformers, and uses flexibility to defer investment. Ensures compliance and releases __MVA. | Yes | SEPD_CV1_PS009219, PS009220, PS009222_Mannington_Bemerton CCT_EJP | Yes | SEPD_CV1_PS009219, PS009220, PS009222_Mannington_Bemerton CCT_CBA | Yes | SEPD_CV1_PS009220_Mannington_Bemerton CCT_CEM
SEPD | PS009222 | New 33kV GIS board at Salisbury BSP SALI BSP (P) | CV1 - Primary Reinforcement | 2. Start in ED2, Complete in ED3 |  | 3. Change of Scope | 2. Yes - ED2 | Isolates Netherhampton and Petersfinger from the ring, upgrades transformers, and uses flexibility to defer investment. Ensures compliance and releases __MVA. | Yes | SEPD_CV1_PS009219, PS009220, PS009222_Mannington_Bemerton CCT_EJP | Yes | SEPD_CV1_PS009219, PS009220, PS009222_Mannington_Bemerton CCT_CBA | No
SHEPD | PH003752 | COLL 33/11kV Transformer H&I (P) | CV1 - Primary Reinforcement | 2. Start in ED2, Complete in ED3 |  | 4. New Scheme | 3. No | Replacement of Coll T1 with 6.3MVA unit, install T2, reinforce 11kV spur, delivering P2/8 compliance and thermal resilience. | Yes | SHEPD_CV1_PH003752_Ardmore_Coll Primary_EJP | Yes | SHEPD_CV1_PH003752_Ardmore_Coll Primary_CBA | No
SHEPD | PH003753 | BEAULY 33kV Circuits H&I (P) | CV1 - Primary Reinforcement | 2. Start in ED2, Complete in ED3 |  | 4. New Scheme | 3. No | Reinforcement of circuits and transformers to resolve thermal overloads and ensure compliance up to 2050. | Yes | SHEPD_CV1_PH003753, PH004352_Beauly_Beauly GSP_EJP | Yes | SHEPD_CV1_PH003753_Beauly_Beauly GSP_CBA | Yes | SHEPD_CV1_PH003753_Beauly_Beauly GSP_CEM
SHEPD | PH003754 | BARVAS 33/11kV Transformer H&I (P) | CV1 - Primary Reinforcement | 2. Start in ED2, Complete in ED3 |  | 4. New Scheme | 3. No | Replacement of Barvas T1 and T2 with 6.3MVA units and contract flexibility to avoid thermal overload until reinforcement can be delivered. | Yes | SHEPD_CV1_PH003754_Ardmore_Barvas Primary_EJP | No |  | No
SHEPD | PH003815 | New Lochmaddy Primary Substation Loch Carnan GSP (P) | CV1 - Primary Reinforcement | 2. Start in ED2, Complete in ED3 |  | 4. New Scheme | 3. No | New primary at Lochmaddy to support ferry terminal and resolve P2/8 compliance, with 11 kV ring reinforcement. | Yes | SHEPD_CV1_PH003815_Ardmore_Admore GSP, Lochmaddy New Primary _EJP | Yes | SHEPD_CV1_PH003815_Ardmore_Admore GSP, Lochmaddy New Primary _CBA | No
SHEPD | PH004221 | Tarland Ring Voltage support - Tarland GSP (P) | CV1 - Primary Reinforcement | 2. Start in ED2, Complete in ED3 |  | 4. New Scheme | 3. No | Major reinforcement and reconfiguration of Tarland Ring, including new circuits and substations, to resolve voltage and thermal constraints and support future growth. | Yes | SHEPD_CV1_PH004221_Tarland_Tarland CCT _EJP | Yes | SHEPD_CV1_PH004221_Tarland_Tarland CCT _CBA | No
SHEPD | PH004224 | Lochailort STATCOM - Fort William GSP (P) | CV1 - Primary Reinforcement | 2. Start in ED2, Complete in ED3 |  | 4. New Scheme | 3. No | Multi-scheme reinforcement installing STATCOMs, OHL and cable upgrades, transformer replacement to resolve voltage and thermal issues under N-1. | Yes | SHEPD_CV1_PH003799, PH003788, PH004224_Fort William_Fort William CCT_EJP | Yes | SHEPD_CV1_PH004224_Fort William_Fort William CCT_CBA | No
SHEPD | PH004345 | Laxay S/S P2 Compliance Laxay (P) / Opt 3 Motts (S) | CV1 - Primary Reinforcement | 2. Start in ED2, Complete in ED3 |  | 4. New Scheme | 3. No | Upgrade of Laxay T1, install T2, new 33kV board, 11kV and 33kV reinforcement for full P2/8 compliance. | Yes | SHEPD_CV1_PH004345_Stornoway_Laxay Primary_EJP | Yes | SHEPD_CV1_PH004345_Stornoway_Laxay Primary_CBA | No
SHEPD | PH004382 | Errochty/ Tummel Bridge Works Integration works Tummel Bridge Grid (P) | CV1 - Primary Reinforcement | 2. Start in ED2, Complete in ED3 |  | 4. New Scheme | 3. No | Integration of Tummel Bridge GSP 33kV Network to new Errochty GSP, releasing __MVA to the distribution network. | Yes | SHEPD_CV1_PH004382_Tummel Bridge_Errochty GSP Integration_EJP | Yes | SHEPD_CV1_PH004382_Tummel Bridge_Errochty GSP Integration_CBA | No
SHEPD | PH004441 | A&W Salen 2, Acharacle, 33/11kV Transformer Reinforcement Salen Primary Substation Mainland (P) / ED2 (S) | CV1 - Primary Reinforcement | 2. Start in ED2, Complete in ED3 |  | 4. New Scheme | 3. No | Replacement of Salen 2 T1 with 4MVA transformer and new primary at Loch Mudle, delivering P2/8 compliance and security of supply. | Yes | SHEPD_CV1_PH004441_Fort William_Salen 2_EJP | No |  | No
SEPD | PS006889 | Fleet 132kV Fault Level Reinforcement FLEET 132KV (P) / FLEET FAULT LEVEL FLEET GSP (S) | CV3 - Fault Level Reinforcement | 2. Start in ED2, Complete in ED3 |  | 4. New Scheme | 3. No | Replaces Fleet 132kV AIS with two GIS substations to resolve fault level issues and enable future demand growth and splitting of the GSP group. | Yes | SEPD_CV3_PS006889_Fleet_Fleet 132kV CB_EJP | Yes | SEPD_CV3_PS006889_Fleet_Fleet 132kV CB_CBA | No
SEPD | PS008838 | Slough/Slough South/Cippenham BSPs Strategic Investment (P) | CV1 - Primary Reinforcement | 2. Start in ED2, Complete in ED3 |  | 4. New Scheme | 3. No | Reinforces three BSPs with new transformers, circuits, and switchgear to resolve thermal and fault level constraints and support growth to 2050. | Yes | SEPD_CV1_PS008838_Iver 132kV_Slough - Slough South - Cippenham BPSs_EJP | Yes | SEPD_CV1_PS008838_Iver 132kV_Slough - Slough South - Cippenham BPSs_CBA | No
SEPD | PS008854 | Park Royal PSS Strategic Investment (P) | CV1 - Primary Reinforcement | 2. Start in ED2, Complete in ED3 |  | 4. New Scheme | 3. No | Upgrades Park Royal to 11kV, adds new transformers and cables, and connects to a new 66kV busbar at Perivale to resolve capacity constraints. | Yes | SEPD_CV1_PS008854_Willesden_Willesden - Park Royal Primary_EJP | No |  | No
SEPD | PS008926 | NHYD22KV BSP Strategic investment (P) | CV1 - Primary Reinforcement | 2. Start in ED2, Complete in ED3 |  | 4. New Scheme | 3. No | Establishes a remote 132kV switchboard to increase capacity, enable voltage rationalisation, and support major load growth. | Yes | SEPD_CV1_PS008926_North Hyde_North Hyde BSP_EJP | No |  | No
SEPD | PS009016 | load related reinforcement EJP (S) / Rowden Melksham (P) | CV1 - Primary Reinforcement | 2. Start in ED2, Complete in ED3 |  | 4. New Scheme | 3. No | Addresses thermal overloads at Rowden Primary and circuits by phased transformer, cable, and switchgear upgrades, using flexibility to defer investment. Releases __MVA by 2030. | Yes | SEPD_CV1_PS009016_Melksham_Rowden Primary_EJP | Yes | SEPD_CV1_PS009016_Melksham_Rowden Primary_CBA | Yes | SEPD_CV1_PS009016_Melksham_Rowden Primary_CEM
SEPD | PS009022 | Gerrards Cross PSS Strategic Investment (P) | CV1 - Primary Reinforcement | 2. Start in ED2, Complete in ED3 |  | 4. New Scheme | 3. No | Reinforces Denham BSP and downstream primaries to resolve thermal overloads and rationalise voltage levels. Delivers __MVA at Denham and __MVA at each primary. | Yes | SEPD_CV1_PS009024, PS009022, PS008844_Iver 132kV_Denham BSP_EJP | Yes | SEPD_CV1_PS009024, PS009022, PS008844_Iver 132kV_Denham BSP_CBA | No
SEPD | PS009024 | Denham Avenue PSS Strategic Investment (P) | CV1 - Primary Reinforcement | 2. Start in ED2, Complete in ED3 |  | 4. New Scheme | 3. No | Reinforces Denham BSP and downstream primaries to resolve thermal overloads and rationalise voltage levels. Delivers __MVA at Denham and __MVA at each primary. | Yes | SEPD_CV1_PS009024, PS009022, PS008844_Iver 132kV_Denham BSP_EJP | Yes | SEPD_CV1_PS009024, PS009022, PS008844_Iver 132kV_Denham BSP_CBA | No
SEPD | PS009030 | Winchester 33kV indooring - Winchester 33kV network (P) | CV3 - Fault Level Reinforcement | 2. Start in ED2, Complete in ED3 |  | 4. New Scheme | 3. No | Installs new indoor switchboard and building to resolve fault level issues and support future connections at Winchester BSP. | Yes | SEPD_CV3_PS009030_Nursling_Winchester BSP_EJP | No |  | No
SEPD | PS009031 | Addition of dual 132kV UG cables from Mannington GSP to Christchurch BSP (P) | CV1 - Primary Reinforcement | 2. Start in ED2, Complete in ED3 |  | 4. New Scheme | 3. No | Reinforces Redhill BSP and 132kV network with new transformers, circuits, and switchgear to resolve thermal and fault level constraints and support future demand. | Yes | SEPD_CV1_PS009031, PS009032_Mannington_Redhill BSP + 132kV CCT + Winton Primary_EJP | Yes | SEPD_CV1_PS009031, PS009032_Mannington_Redhill BSP + 132kV CCT + Winton Primary_CBA | No
SEPD | PS009032 | Reinforcement of Winton 33/11kV transformers and Install 33 kV switch board at WINT PSS Winton Primary (P) | CV1 - Primary Reinforcement | 2. Start in ED2, Complete in ED3 |  | 4. New Scheme | 3. No | Reinforces Redhill BSP and 132kV network with new transformers, circuits, and switchgear to resolve thermal and fault level constraints and support future demand. | Yes | SEPD_CV1_PS009031, PS009032_Mannington_Redhill BSP + 132kV CCT + Winton Primary_EJP | Yes | SEPD_CV1_PS009031, PS009032_Mannington_Redhill BSP + 132kV CCT + Winton Primary_CBA | No
SEPD | PS009046 | 132kV CBs reinforcement at Mannington GSP (P) / Outdoor to indoor busbar transformation work (S) | CV3 - Fault Level Reinforcement | 2. Start in ED2, Complete in ED3 |  | 4. New Scheme | 3. No | Reinforces Mannington GSP and 132kV network with new transformers, circuits, and switchgear to resolve thermal and fault level constraints and support future demand. | Yes | SEPD_CV1, CV3_PS009046, PS009212_Mannington_Mannington GSP_EJP | Yes | SEPD_CV3_PS009046_Mannington_Mannington GSP_CBA | No
SEPD | PS009057 | Lovedean GSP 132kV CBs reinfrocement Lovedean GSP (P) / Outdoor to indoor busbar (S) | CV3 - Fault Level Reinforcement | 2. Start in ED2, Complete in ED3 |  | 4. New Scheme | 3. No | Installs new GIS switchgear, new circuits, and transfers Wymering BSP to Lovedean to resolve fault level and thermal constraints. | Yes | SEPD_CV3_PS009057, PS009080_Lovedean_Loverdean GSP_EJP | Yes | SEPD_CV3_PS009057, PS009080_Lovedean_Loverdean GSP_CBA | No
SEPD | PS009152 | EJP Rose Hill 33kV network reinforcement (P) | CV1 - Primary Reinforcement | 2. Start in ED2, Complete in ED3 |  | 4. New Scheme | 3. No | Installs new transformer, circuits, and switchgear, upgrades Rose Hill, and uses flexibility to defer investment, ensuring compliance and capacity. | Yes | SEPD_CV1_PS009152, PS009135_Cowley_Cowley Local Main and 132kV CCT_EJP | Yes | SEPD_CV1_PS009152, PS009135_Cowley_Cowley Local Main and 132kV CCT_CBA | Yes | SEPD_CV1_PS009152_Cowley_Cowley Local Main and 132kV CCT_CEM SEPD_CV1_PS009152_Cowley_Cowley Local Main and 132kV CCT_CEM2
SEPD | PS009162 | Nursling 132kV indoor switchroom - Nursling GSP Substation (P) | CV3 - Fault Level Reinforcement | 2. Start in ED2, Complete in ED3 |  | 4. New Scheme | 3. No | Installs two new indoor switchboards to resolve fault level issues and enable future transformer and customer connections at Nursling GSP. | Yes | SEPD_CV3_PS009162_Nursling_Nursling 132kV_EJP | No |  | No
SEPD | PS009168 | Horndean dual circuits, Waterlooville 33kV switchgear, Fort Widley 33kV switchgear Fort Widley (P) | CV1 - Primary Reinforcement | 2. Start in ED2, Complete in ED3 |  | 4. New Scheme | 3. No | Transfers Horndean to Fort Widley, upgrades circuits and transformers, and uses flexibility to defer investment. Releases __MVA and supports compliance to 2050. | Yes | SEPD_CV1_PS009167, PS009168_Lovedean_Fort Widley - Horndean - Waterlooville_EJP | Yes | SEPD_CV1_PS009167, PS009168_Lovedean_Fort Widley - Horndean - Waterlooville_CBA | Yes | SEPD_CV1_PS009168_Lovedean_Fort Widley - Horndean - Waterlooville_CEM
SEPD | PS009175 | 33kV AIS - GIS Alton BSP (P) | CV1 - Primary Reinforcement | 2. Start in ED2, Complete in ED3 |  | 4. New Scheme | 3. No | Converts 33kV AIS to GIS to resolve space constraints, enable future expansion, and support load growth and new connections. | Yes | SEPD_CV1_PS009175_Fleet_Alton BSP_EJP | Yes | SEPD_CV1_PS009175_Fleet_Alton BSP_CBA | No
SEPD | PS009177 | Coxmoor Wood 132/33kV BSP Load Related Reinforcement Coxmoor Wood BSP (P) / COXW 3rd Transformer (S) | CV1 - Primary Reinforcement | 2. Start in ED2, Complete in ED3 |  | 4. New Scheme | 3. No | Adds a third transformer and GIS switchgear to Coxmoor Wood BSP, resolving P2/8 compliance issues and enabling future expansion. Delivers up to __MVA. | Yes | SEPD_CV1_PS009177_Fleet_Coxmoor Wood 132kV_EJP | Yes | SEPD_CV1_PS009177_Fleet_Coxmoor Wood 132kV_CBA | No
SEPD | PS009198 | 33 KV (S) / Whitchurch and Barton Stacey primary substations (P) | CV1 - Primary Reinforcement | 2. Start in ED2, Complete in ED3 |  | 4. New Scheme | 3. No | Resolves thermal overloads and single-circuit supply risks by installing a new cable, transformer upgrades, and flexibility. Ensures compliance and releases up to __MVA by 2028, with further upgrades in 2035. | Yes | SEPD_CV1_PS009198_Melksham_Whitchurch and Barton Stacey Primaries_EJP | Yes | SEPD_CV1_PS009198_Melksham_Whitchurch and Barton Stacey Primaries_CBA | Yes | SEPD_CV1_PS009198_Melksham_Whitchurch and Barton Stacey Primaries_CEM
SEPD | PS009205 | Bilsham PSS 3rd Transformer, new 33kV switchgear and 11kV switchgear reinforcement (P) | CV1 - Primary Reinforcement | 2. Start in ED2, Complete in ED3 |  | 4. New Scheme | 3. No | Adds new 33kV switchgear, a 3rd transformer, and replaces 11kV switchboard to address thermal constraints and support growth to 2050. | Yes | SEPD_CV1_PS009205_Lovedean_Bilsham Primary_EJP | Yes | SEPD_CV1_PS009205_Lovedean_Bilsham Primary_CBA | No
SEPD | PS009212 | Addition of dual 132kV cct from MANN GSP to SHAF BSP Shaftesbury BSP (P) | CV1 - Primary Reinforcement | 2. Start in ED2, Complete in ED3 |  | 4. New Scheme | 3. No | Reinforces Mannington GSP and 132kV network with new transformers, circuits, and switchgear to resolve thermal and fault level constraints and support future demand. | Yes | SEPD_CV1, CV3_PS009046, PS009212_Mannington_Mannington GSP_EJP | No |  | No
SEPD | PS009225 | Yarnton BSP EJP - Network Reinforcement Yarnton BSP (P) | CV1 - Primary Reinforcement | 2. Start in ED2, Complete in ED3 |  | 4. New Scheme | 3. No | Adds a new 132kV circuit and upgrades switchgear to resolve thermal overloads, using flexibility to maintain compliance during build-out. Releases __MVA. | Yes | SEPD_CV1_PS009225_Cowley_Cowley - Yarnton CCT_EJP | No |  | No
SEPD | PS009534 | Botley Wood BSP 33kV CB installation BOTLEY WOOD BSP (S) / North Fareham PSS 33kV Busbar installation and 33kV ccts between BOTW BSP and NFAR PSS NORTH FAREHAM PSS (P) | CV1 - Primary Reinforcement | 2. Start in ED2, Complete in ED3 |  | 4. New Scheme | 3. No | Transfers North Fareham PSS, installs new circuits and GIS busbars, reinforces circuits, and uses flexibility to defer investment, ensuring compliance and capacity to 2050. | Yes | SEPD_CV1_PS009534_Lovedean_Botley Wood BSP + North Fareham Primary_EJP | Yes | SEPD_CV1_PS009534_Lovedean_Botley Wood BSP + North Fareham Primary_CBA | Yes | SEPD_CV1_PS009534_Lovedean_Botley Wood BSP + North Fareham Primary_CEM SEPD_CV1_PS009534_Lovedean_Botley Wood BSP + North Fareham Primary_CEM2
SHEPD | PH004472 | HIGH P2 Compliance Lairg Primary (P) | CV1 - Primary Reinforcement | 3. Feasibility & Consents only ED2 |  | 2. Existing Scheme | 2. Yes - ED2 |  | No |  | No |  | No
SEPD | PS007633 | Egham Primary Substation Reinforcement Egham (P) | CV1 - Primary Reinforcement | 3. Feasibility & Consents only ED2 |  | 2. Existing Scheme | 2. Yes - ED2 |  | No |  | No |  | No
SEPD | PS007693 | Osney 132 kV Circuit Primary Reinforcement (P) | CV1 - Primary Reinforcement | 3. Feasibility & Consents only ED2 |  | 2. Existing Scheme | 2. Yes - ED2 |  | No |  | No |  | No
SEPD | PS007701 | Beaconsfield Transformers and Circuit Primary Reinforcement (P) | CV1 - Primary Reinforcement | 3. Feasibility & Consents only ED2 |  | 2. Existing Scheme | 2. Yes - ED2 |  | No |  | No |  | No
SEPD | PS009091 | Portsmouth 3rd Grid Tx and 3rd 132kV cct PORTSMOUTH BSP (P) | CV1 - Primary Reinforcement | 3. Feasibility & Consents only ED2 |  | 2. Existing Scheme | 2. Yes - ED2 |  | No |  | No |  | No
SHEPD | PH004321 | Tressady 33/11kV Transformer Tressady Primary (P) | CV1 - Primary Reinforcement | 3. Feasibility & Consents only ED2 |  | 3. Change of Scope | 2. Yes - ED2 |  | No |  | No |  | No
SEPD | PS007688 | Fulscot 33kV Circuit Reinforcement (P) | CV1 - Primary Reinforcement | 3. Feasibility & Consents only ED2 |  | 3. Change of Scope | 2. Yes - ED2 |  | No |  | No |  | No
SHEPD | PH004344 | Gisla S/S P2 Compliance - H&I (P) | CV1 - Primary Reinforcement | 3. Feasibility & Consents only ED2 |  | 4. New Scheme | 2. Yes - ED2 |  | No |  | No |  | No
SHEPD | PH002742 | Queens Lane North 11kV Switchboard Primary Substation (P) | CV1 - Primary Reinforcement | 3. Feasibility & Consents only ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SHEPD | PH003788 | Fort William 33KV circuit 3L5 SCAL (P) | CV1 - Primary Reinforcement | 3. Feasibility & Consents only ED2 |  | 4. New Scheme | 3. No | Multi-scheme reinforcement installing STATCOMs, OHL and cable upgrades, transformer replacement to resolve voltage and thermal issues under N-1. | Yes | SHEPD_CV1_PH003799, PH003788, PH004224_Fort William_Fort William CCT_EJP | No |  | No
SHEPD | PH003799 | Inverlochy Circuits - Fort William 33kV Circuits SCAL (P) | CV1 - Primary Reinforcement | 3. Feasibility & Consents only ED2 |  | 4. New Scheme | 3. No | Multi-scheme reinforcement installing STATCOMs, OHL and cable upgrades, transformer replacement to resolve voltage and thermal issues under N-1. | Yes | SHEPD_CV1_PH003799, PH003788, PH004224_Fort William_Fort William CCT_EJP | No |  | No
SHEPD | PH004206 | Nostie Bridge 11kV circuits - Broadford GSP (P) | CV1 - Primary Reinforcement | 3. Feasibility & Consents only ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SHEPD | PH004213 | OLDMELDRUM 33/11kV Transformer Kintore GSP (P) | CV1 - Primary Reinforcement | 3. Feasibility & Consents only ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SHEPD | PH004214 | Oldmeldrum Circuit Review Kintore 301 (P) | CV1 - Primary Reinforcement | 3. Feasibility & Consents only ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SHEPD | PH004215 | Banchory Transformer Upgrade Kintore GSP (P) | CV1 - Primary Reinforcement | 3. Feasibility & Consents only ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SHEPD | PH004216 | NEWTONHILL 33/11kV Transformer Redmoss GSP (P) | CV1 - Primary Reinforcement | 3. Feasibility & Consents only ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SHEPD | PH004218 | Scalloway, Setter Sandwick and Sumburgh - Shetland GSP (P) | CV1 - Primary Reinforcement | 3. Feasibility & Consents only ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SHEPD | PH004220 | Tarland Interconnections Circuits - Tarland GSP (P) | CV1 - Primary Reinforcement | 3. Feasibility & Consents only ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SHEPD | PH004226 | Calvine Primary TX - Tummel Bridge Grid (P) | CV1 - Primary Reinforcement | 3. Feasibility & Consents only ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SHEPD | PH004301 | ASHLUDIE 33/11kV Transformer - Milton of Craigie GSP (P) | CV1 - Primary Reinforcement | 3. Feasibility & Consents only ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SHEPD | PH004307 | DORNOCH 33/11kV Transformer - Brora GSP (P) | CV1 - Primary Reinforcement | 3. Feasibility & Consents only ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SHEPD | PH004308 | MONTROSE NORTH 33/11kV Transformer - Bridge of Dun (P) | CV1 - Primary Reinforcement | 3. Feasibility & Consents only ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SHEPD | PH004315 | Dunoon 33kV Circuits (P) | CV1 - Primary Reinforcement | 3. Feasibility & Consents only ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SHEPD | PH004316 | Raigmore Inverness GSP (P) | CV1 - Primary Reinforcement | 3. Feasibility & Consents only ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SHEPD | PH004323 | Grudie Bridge 3L5 33kV Circuits Grudie Bridge (P) | CV1 - Primary Reinforcement | 3. Feasibility & Consents only ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SHEPD | PH004352 | Connon Bridge Beauly GSP (P) | CV1 - Primary Reinforcement | 3. Feasibility & Consents only ED2 |  | 4. New Scheme | 3. No | Reinforcement of circuits and transformers to resolve thermal overloads and ensure compliance up to 2050. | Yes | SHEPD_CV1_PH003753, PH004352_Beauly_Beauly GSP_EJP | No |  | No
SHEPD | PH004409 | Forres 33/11kV Network Nairn GSP (P) | CV1 - Primary Reinforcement | 3. Feasibility & Consents only ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SHEPD | PH004435 | Hatston 33kV Substation Finstown GSP (P) | CV1 - Primary Reinforcement | 3. Feasibility & Consents only ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SHEPD | PH004451 | Kinloch 33/11kV Network Taynuilt GSP (P) | CV1 - Primary Reinforcement | 3. Feasibility & Consents only ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SEPD | PS007691 | Chalvey Strategic Investment (P) | CV1 - Primary Reinforcement | 3. Feasibility & Consents only ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SEPD | PS007721 | Birdham Primary Transformer Reinforcement (P) | CV1 - Primary Reinforcement | 3. Feasibility & Consents only ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SEPD | PS008836 | Staines BSP Strategic Investment (P) | CV1 - Primary Reinforcement | 3. Feasibility & Consents only ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SEPD | PS008848 | Copley Dene PSS Strategic Investment (P) | CV1 - Primary Reinforcement | 3. Feasibility & Consents only ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SEPD | PS008852 | Bridge Road PSS Strategic Investment (P) | CV1 - Primary Reinforcement | 3. Feasibility & Consents only ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SEPD | PS008857 | BATH ROAD EAST PSS Strategic investment (P) | CV1 - Primary Reinforcement | 3. Feasibility & Consents only ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SEPD | PS009007 | 132kV Fawley North OD CB Fawley North (P) | CV1 - Primary Reinforcement | 3. Feasibility & Consents only ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SEPD | PS009010 | 1 x new cct AND 1 x 33kV outdoor CB Netley Common BSP (P) / 7 x 33kV indoor CB Townhill Park Primary (S) | CV1 - Primary Reinforcement | 3. Feasibility & Consents only ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SEPD | PS009012 | Alderton Melksham (P) / Load related reinforcement EJP (S) | CV1 - Primary Reinforcement | 3. Feasibility & Consents only ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SEPD | PS009033 | Arnewood BSP 132 kV and 33kV indoor switch rooms. Addition of 3rd BSP transformer (P) | CV1 - Primary Reinforcement | 3. Feasibility & Consents only ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SEPD | PS009042 | SPRINGFIELD ROAD PSS Strategic investment (P) | CV1 - Primary Reinforcement | 3. Feasibility & Consents only ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SEPD | PS009058 | Emsworth 33/11kV S/S Relocation LV+Civil Works Emsworth S/S New Plot (P) | CV1 - Primary Reinforcement | 3. Feasibility & Consents only ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SEPD | PS009080 | LOVE GSP (S) / Lovedean 3 new 132kV circuits to Wymering BSP, transfer from FWID (P) / LOVE GSP (S) (P) | CV1 - Primary Reinforcement | 3. Feasibility & Consents only ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SEPD | PS009166 | Horndean Primary - 33kV - Transformer Addition Horndean (P) | CV1 - Primary Reinforcement | 3. Feasibility & Consents only ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SEPD | PS009189 | Brockhurst PSS 3rd Transformer and 3rd 33kV Circuit BROCKHURST PSS (P) | CV1 - Primary Reinforcement | 3. Feasibility & Consents only ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SEPD | PS009190 | Hoeford PSS 3rd Transformer HOEFORD PSS (P) | CV1 - Primary Reinforcement | 3. Feasibility & Consents only ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SEPD | PS009191 | Titchfield PSS 2x Transformer Replacement and 33kV switchgear replacement TITCHFIELD PSS (P) | CV1 - Primary Reinforcement | 3. Feasibility & Consents only ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SEPD | PS009207 | Chalcraft Lane New PSS (P) | CV1 - Primary Reinforcement | 3. Feasibility & Consents only ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SEPD | PS009210 | Fareham BSP 33kV Busbar Reinforcement FAREHAM BSP (P) | CV1 - Primary Reinforcement | 3. Feasibility & Consents only ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SEPD | PS009217 | Cirencester - Minety Village 33kv circuit Reinforcement CIRE - MINV (S) / Cirencester Cricklade 33kV network reinforcement EJP CIRE - CRIC (P) | CV1 - Primary Reinforcement | 3. Feasibility & Consents only ED2 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SHEPD | PH003794 | Cromalt and Inverary 33/11kV Transformer Replacements Argyll and Bute (P) | CV1 - Primary Reinforcement | 4. Design and Build in ED3 |  | 3. Change of Scope | 2. Yes - ED2 | Multi-scheme reinforcement for Cromalt/Inveraray, Lochgilphead/Carradale, and Islay, addressing thermal, voltage, and P2/8 issues. | Yes | SHEPD_CV1_PH003794, PH004419, PH004429_PORT ANN_PORT ANN GSP_EJP | No |  | No
SHEPD | PH004211 | ELGIN 33 kV Circuits Elgin GSP (P) | CV1 - Primary Reinforcement | 4. Design and Build in ED3 |  | 3. Change of Scope | 2. Yes - ED2 |  | No |  | No |  | No
SHEPD | PH004310 | STRICHEN 33 kV Circuits - Strichen GSP (P) | CV1 - Primary Reinforcement | 4. Design and Build in ED3 |  | 3. Change of Scope | 2. Yes - ED2 |  | No |  | No |  | No
SHEPD | PH004322 | Drumrunie Transformer Drumrunie Primary (P) | CV1 - Primary Reinforcement | 4. Design and Build in ED3 |  | 3. Change of Scope | 2. Yes - ED2 |  | No |  | No |  | No
SHEPD | PH004367 | Kilmelford & Kilninver 33/11kV Network Taynuilt GSP (P) | CV1 - Primary Reinforcement | 4. Design and Build in ED3 |  | 3. Change of Scope | 2. Yes - ED2 |  | No |  | No |  | No
SHEPD | PH004368 | Dervaig 33kV Circuits Taynuilt GSP (P) | CV1 - Primary Reinforcement | 4. Design and Build in ED3 |  | 3. Change of Scope | 2. Yes - ED2 |  | No |  | No |  | No
SHEPD | PH004419 | Port Askaig 33kV circuit Isle of Islay, Argyll and Bute (P) | CV1 - Primary Reinforcement | 4. Design and Build in ED3 |  | 3. Change of Scope | 2. Yes - ED2 | Multi-scheme reinforcement for Cromalt/Inveraray, Lochgilphead/Carradale, and Islay, addressing thermal, voltage, and P2/8 issues. | Yes | SHEPD_CV1_PH003794, PH004419, PH004429_PORT ANN_PORT ANN GSP_EJP | No |  | No
SHEPD | PH004279 | Dufftown Primary Transformer Replacement Dufftown Primary (P) | CV1 - Primary Reinforcement | 4. Design and Build in ED3 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SHEPD | PH004302 | EJP/SHEPD/PERS/STON/001 Persley GSP (P) | CV1 - Primary Reinforcement | 4. Design and Build in ED3 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SHEPD | PH004320 | Strathleven 33kV circuits Strathleven GSP (P) | CV1 - Primary Reinforcement | 4. Design and Build in ED3 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SHEPD | PH004325 | Midmar Transformer Reinforcement Kintore GSP (P) | CV1 - Primary Reinforcement | 4. Design and Build in ED3 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SHEPD | PH004412 | Kepculloch 33/11kV Substation Strathleven GSP (P) | CV1 - Primary Reinforcement | 4. Design and Build in ED3 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SHEPD | PH004433 | Broadford 303 - Broadford GSP (P) | CV1 - Primary Reinforcement | 4. Design and Build in ED3 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SEPD | PS007685 | Berinsfield 33kV Circuit Reinforcement (P) | CV1 - Primary Reinforcement | 4. Design and Build in ED3 |  | 4. New Scheme | 3. No |  | No |  | No |  | No
SEPD | PS009056 | FAY294 Addendum Axminster - Yeovil 132kV oil filled cable replacement on 132kV circuit 2 (P) | CV1 - Primary Reinforcement | 4. Design and Build in ED3 |  | 4. New Scheme | 3. No |  | No |  | No |  | No